## Sheet1
Completed | Item | Week
2019-05-13 | Capstone Proposal | 1
Classic Control (Discrete Actions)
2019-05-18 | Initial framework for OpenAI training | 1
2019-05-19 | Discretization and Tile Agents for Gym MountainCar | 1
2019-05-19 | Discretization and Tile Agents for Gym Cartpole | 1
2019-05-19 | Discretization and Tile Agents for Gym Acrobat | 1
Classic Control (Continous Actions)
2019-05-21 | Deep Q Agent with TF for Gym Cartpole | 2
2019-05-21 | Deep Q Agent with TF for Gym Acrobat | 2
2019-05-21 | Deep Q Agent with TF for Gym Pendulum | 2
2019-05-24 | DDPG Agent for Gym MountainCarContinous | 2
2019-05-24 | DDPG Agent for Gym Pendulum | 2
2019-05-25 | Design stardard training/test/visualization workflow for all env/agents | 2
| Cleanup QLearner (discrete/tiles) to align with standard workflow | 2
| Cleaup DDPG code to align with standard workflow | 2
| DQNv2.0 (Keras instead of TF for simplicity) | 2 | https://towardsdatascience.com/reinforcement-learning-w-keras-openai-dqns-1eed3a5338c
| Align QQNv2.0 Code with standard workflow | 2 | https://towardsdatascience.com/reinforcement-learning-w-keras-openai-actor-critic-models-f084612cfd69
Box 2D (Continous Actions)
| Install Linux with OpenAI & Keras for Box2D and Atari Support | 3
| BipedalWalkerV2 | 3
| LunarLander-V2 | 3
| CarRacing-V0 | 3
3